## Executive Summary
Jamaica eTitles – SMD Spatial Decision Register
Purpose: separate transaction validation decisions from authoritative cadastral / Parcel Fabric governance decisions.
Area | Total Decisions | Open / Partial | Critical Open / Partial
A. Transaction Validation | 17 | 12 | 5
B. Cadastral Governance | 27 | 27 | 18
Three decision gates to formalize
Gate | Question | Primary Area | Expected Output
1. Technical Validity | Is the submitted survey internally and mathematically correct? | Compute | Pass / Warning / Fail
2. Cadastral Compatibility | Does the validated survey agree with existing cadastral and registry evidence? | Compare | Compatible / Conflict / Review
3. Authoritative Change | If there is a conflict, what is correct and what are we authorized to change? | Cadastral Change Assessment | Approved action before Parcel Fabric / Enterprise post
Recommended control flow
Compute → Compare → Cadastral Change Assessment → Authorization → Parcel Fabric Update → Independent QA → Reconcile/Post
Core principle
The software may detect and assist; authoritative cadastral/legal precedence requires an accountable human decision, evidence, approval, and audit trail.

## A_Transaction Validation
ID | Decision / Question | Decision Type | Priority | Current Position / Assumption | Decision Required | Recommended Direction | Decision Owner | Impact if Undefined | Status | Notes / Final Decision
A-01 | What exact transaction payload is received from Innola into ArcGIS Pro? | Technical | High | Transaction ID, transaction type, document references and execution context are expected. | Confirm the minimum mandatory payload, affected parcel references, rules/configuration profile, and submission type. | Define a versioned input contract between Innola and the ArcGIS Pro Add-In. | Joint Project Team | Inconsistent execution context; tasks may not know what data or rules apply. | Closed
A-02 | What constitutes a complete submission before GIS processing starts? | Business Rule | High | PDF/plan, CAD where applicable, computer sheet/coordinates and supporting documents are expected by transaction type. | Approve the required-document matrix by SMD transaction and submission mode. | Enforce completeness before Compute; missing mandatory items return for correction. | NLA / SMD | Invalid or incomplete submissions enter Compute and generate avoidable examiner work. | Partially Defined
A-03 | Which authoritative/reference layers must be loaded for each transaction? | Data Policy | High | CadMap, CadIndex, Parcel Fabric, control data and selected LTD/LVD references are anticipated. | Confirm the authoritative/reference dataset list per transaction and which are read-only versus editable. | Publish a transaction-to-dataset matrix and layer role definition. | NLA / SMD | Different examiners may compare against different sources and reach inconsistent conclusions. | Partially Defined | Currently Legal Cadastre and Fiscal Cadastre
A-04 | Which structure checks are mandatory? | Business Rule | High | Required plan elements, expected CAD layers, coordinates, CRS and metadata checks are identified conceptually. | Approve the final structure-validation checklist and severity of each rule. | Group checks into mandatory, warning and informational categories. | NLA / SMD | No consistent gate before geometry analysis. | Closed
A-05 | Which geometry checks are mandatory? | Business Rule | High | Traverse/closure, bearings, distances, line direction, tie lines and control references are in scope. | Approve tolerances, thresholds and pass/fail criteria. | Parameterize tolerances as business rules rather than hard-code them. | NLA / SMD | Different users may apply different technical tolerances. | Closed
A-06 | Which topology/data-integrity checks are mandatory? | Business Rule | High | Connectivity, duplicates, gaps/overlaps and invalid geometry are expected checks. | Define which topology conditions block processing versus create warnings. | Use a standard topology rule set with severity classification. | NLA / SMD | Technically questionable geometry could advance inconsistently. | Closed
A-07 | How should CAD-to-PDF inconsistencies be handled? | Business Rule | Medium | Digital submissions should be visually/structurally consistent across submitted representations. | Define whether mismatch is blocking, warning, or examiner override. | Treat material boundary/dimension mismatch as blocking; minor cartographic differences as reviewable warnings. | NLA / SMD | Conflicting source representations may be accepted without a consistent rule. | Open
A-08 | How do we distinguish a submission error from an existing cadastral-data problem? | Governance | Critical | The current design detects conflicts but does not fully classify whether the new submission or legacy data is wrong. | Define discrepancy categories and the workflow path for each. | Introduce explicit classification: Submission Error / Legacy Data Issue / Cross-System Conflict / Undetermined. | NLA Joint | Valid surveys may be rejected because legacy data is wrong, or legacy errors may be overwritten without authority. | Open
A-09 | What happens when a mathematically valid survey conflicts with CadMap/CadIndex/Parcel Fabric? | Governance | Critical | Compare identifies the conflict, but the decision path is not fully defined. | Define escalation, required evidence and who determines whether the existing cadastre is wrong. | Route to Cadastral Change Assessment rather than directly editing Enterprise data. | NLA / SMD | High risk of inconsistent or unauthorized cadastral changes. | Open
A-10 | Can an examiner override a failed/warning validation? | Governance | Critical | Human-in-the-loop review is expected, but override authority is not clearly defined. | Define which rules are non-overridable, who may override others, and what evidence is mandatory. | Require named role, reason code, comments and supporting evidence for every override. | NLA / SMD | Automated controls can be bypassed without accountability. | Open
A-11 | What are the formal Compute outcomes? | Technical | Medium | PASS / WARNING / FAIL are already used conceptually. | Confirm statuses and mapping to workflow actions. | Use PASSED, WARNING, FAILED, NEEDS_REVIEW with deterministic next actions. | Joint Project Team | Registered in the report attached to the transaction | Partially Defined
A-12 | When may Compute proceed to Compare? | Business Rule | High | Clean results should proceed; handling of warnings and legacy conflicts is unresolved. | Define gate criteria by severity and exception type. | Allow PASS and approved WARNING; block FAIL; route legacy-data conflicts to review. | NLA / SMD | Transactions may advance with unresolved technical issues. | Closed
A-13 | What Compare findings block the transaction? | Business Rule | Critical | Overlap, dual registration, boundary conflicts and cross-system inconsistencies can be discovered. | Define blocking versus reviewable findings and required escalation. | Create a Compare decision matrix with severity and disposition. | NLA / SMD | Potential legal/cadastral conflicts may be handled inconsistently. | Open
A-14 | What is the hierarchy when CadMap, CadIndex, title/registry and LVD information disagree? | Cross-Division | Critical | No complete authoritative-source hierarchy has been established for all conflict scenarios. | Approve the evidence hierarchy and which division owns each class of discrepancy. | Document legal, cadastral and fiscal authority separately; do not treat all layers as equivalent. | NLA Joint | Cross-system discrepancies cannot be resolved consistently. | Open
A-15 | Who confirms technical completion of Compute/Compare? | Governance | High | A Plan Examiner performs/reviews technical work, but final authority needs role confirmation. | Name the role that accepts technical completion and any cases requiring senior review. | Use role-based completion with escalation thresholds. | NLA / SMD | No accountable sign-off point before authoritative change decisions. | Open
A-16 | What outputs must be returned to Innola? | Technical | High | Status, validation results, logs and artifacts are expected. | Finalize the output contract including affected parcels, discrepancy class, evidence and recommended action. | Return structured JSON/status plus links to reports/workspace artifacts. | Joint Project Team | Workflow cannot make deterministic routing decisions. | Partially Defined | Trnumber, result from PE, neigbords
A-17 | What must be retained for audit and reproducibility? | Governance | High | Transaction workspace, logs, user/time, validation outputs and results are conceptually required. | Approve retention contents and period. | Retain input references, rule version, execution logs, before/after geometry, decisions and approvals. | NLA Joint | Unable to reconstruct why a spatial decision was made. | Partially Defined

## B_Cadastral Governance
ID | Decision / Question | Decision Type | Priority | Current Position / Assumption | Decision Required | Recommended Direction | Decision Owner | Impact if Undefined | Status | Notes / Final Decision
B-01 | Who determines that an Enterprise parcel requires change? | Governance | Critical | Compute/Compare may identify a discrepancy, but authority to determine the cadastral treatment is not clearly assigned. | Name the role that converts a technical finding into an authorized cadastral-change proposal. | Plan Examiner identifies; Senior/Chief cadastral authority determines proposed treatment. | NLA / SMD | No accountable decision-maker for authoritative parcel changes. | Open
B-02 | Can the Plan Examiner directly modify authoritative Enterprise parcel data? | Governance | Critical | The design uses transaction/versioned workspaces, but direct authoritative-edit permissions need explicit policy. | Define maker privileges and prohibit or allow direct edits by scenario. | Examiner should edit only a transaction/version workspace, not post directly to authoritative data. | NLA / SMD | Unauthorized or premature changes may reach production. | Open
B-03 | Who approves a geometry adjustment? | Governance | Critical | Review/approval is conceptually required but role and thresholds are not final. | Name approving role and define what qualifies as a minor adjustment. | Senior cadastral reviewer approves; maker cannot self-approve. | NLA / SMD | Small changes may accumulate without consistent oversight. | Open
B-04 | Who approves a geometry replacement? | Governance | Critical | Replacement is higher risk than a normal adjustment and is not clearly governed. | Define approval level and supporting evidence. | Require senior/manager approval plus explicit reason and before/after comparison. | NLA / SMD | Existing authoritative geometry could be overwritten without sufficient authority. | Open
B-05 | When is a parcel considered corrected versus replaced? | Data Policy | Critical | Terminology and lifecycle effects are not fully defined. | Define correction, adjustment, replacement, retirement, subdivision and amalgamation. | Adopt formal cadastral lifecycle definitions tied to PID/lineage rules. | NLA / SMD | Inconsistent PID history and lineage. | Open
B-06 | When can an existing PID retain its identity after geometry change? | Data Policy | Critical | PID persistence rules are not fully defined. | Define allowable geometry-change threshold/type for retaining PID. | Retain PID only where legal parcel identity is unchanged; create lineage event for geometry correction. | NLA / SMD | Incorrect parcel identity continuity or unnecessary PID proliferation. | Open
B-07 | When must a new PID be created and the prior parcel retired? | Data Policy | Critical | Subdivision/amalgamation clearly imply lifecycle changes, but full rule set is pending. | Approve PID creation/retirement rules for subdivision, merge, replacement and boundary redefinition. | Never reuse retired PID; preserve parent-child lineage. | NLA / SMD | Broken parcel lineage and downstream registry/valuation mismatches. | Open
B-08 | Who approves subdivision and parent-parcel retirement? | Governance | High | Expected workflow exists conceptually, but authority should be explicit. | Name maker/checker/approver roles. | Require approved survey/transaction evidence and independent cadastral approval. | NLA / SMD | Child parcels may be created without controlled retirement of parent. | Open
B-09 | Who approves amalgamation/merge of parcels? | Governance | High | Merge mechanics are known technically, but business authority needs definition. | Define evidence, ownership/title prerequisites and approving role. | Do not merge solely because geometries touch; require authorized transaction and legal/cadastral basis. | NLA Joint | Incorrect legal parcels may be collapsed into one spatial feature. | Open
B-10 | Who approves a boundary adjustment affecting two or more active parcels? | Cross-Division | Critical | This can affect multiple legal/fiscal relationships and is not sufficiently governed. | Define required evidence and whether LTD/LVD consultation is mandatory. | Escalate multi-parcel boundary adjustments for senior cadastral review and cross-system impact check. | NLA Joint | One parcel can be corrected at the expense of another without coordinated approval. | Open
B-11 | What happens when two approved surveys overlap? | Governance | Critical | No deterministic rule can safely choose one automatically. | Define investigation and adjudication/escalation route. | Stop posting; preserve both evidence sets; escalate to designated cadastral/legal authority. | NLA Joint | Risk of dual registration or unauthorized preference between legal surveys. | Open
B-12 | What happens when existing Enterprise parcels overlap each other before the new transaction? | Data Policy | Critical | Legacy overlaps are known to exist. | Define whether transaction processing may proceed, and how legacy discrepancy is recorded/resolved. | Do not silently fix during unrelated transaction; create linked legacy-correction case unless directly required. | NLA / SMD | New transaction becomes an uncontrolled cleanup vehicle for historical errors. | Open
B-13 | Which dataset is authoritative for legal boundary decisions? | Cross-Division | Critical | CadMap, CadIndex, Parcel Fabric, survey plans, title records and valuation data may conflict. | Define legal/cadastral/fiscal source hierarchy and evidence rules. | Separate legal authority from spatial operational layer; approved survey/legal record should drive authorized correction, not simply latest GIS geometry. | NLA Joint | Conflicts cannot be resolved consistently or defensibly. | Open
B-14 | If title/registry information conflicts with GIS geometry, who resolves it? | Cross-Division | Critical | Cross-division coordination is required but detailed responsibility is pending. | Define LTD/SMD referral and decision ownership. | SMD owns spatial analysis; LTD owns legal registry interpretation; unresolved cases require joint disposition. | NLA Joint | Spatial update may contradict the legal register. | Open
B-15 | If LVD fiscal parcel geometry conflicts with SMD cadastral geometry, who owns the correction? | Cross-Division | High | Legal and fiscal parcel models serve different purposes. | Define ownership and synchronization rule. | SMD controls cadastral/legal geometry; LVD corrects fiscal representation based on approved cadastral outcome where applicable. | NLA Joint | Fiscal and cadastral layers diverge further. | Open
B-16 | Must every authoritative parcel change use maker-checker approval? | Governance | Critical | Maker-checker is a stated design principle but exceptions are not fully defined. | Approve mandatory checker policy and any low-risk exceptions. | Require maker-checker for all geometry changes; only metadata-only low-risk changes may use simplified approval if NLA agrees. | NLA / SMD | Single-user changes undermine control and auditability. | Partially Defined
B-17 | Can the reviewer modify the maker's edits directly? | Governance | High | Not defined. | Decide whether reviewer may edit, or only approve/reject/return. | Reviewer should normally return for correction; if reviewer edits, system should record reviewer as a new maker action requiring re-validation. | NLA / SMD | Blurred accountability for who made the final geometry. | Open
B-18 | What happens when reviewer disagrees with the proposed cadastral action? | Governance | High | Redo/return is conceptually anticipated. | Define statuses, comments, escalation and rework loop. | Return to maker with mandatory reason; escalate unresolved disputes to designated senior authority. | NLA / SMD | Disagreements can stall informally outside the system. | Open
B-19 | Which changes require a second/high-risk approval? | Governance | High | No risk-tier approval model is defined. | Identify high-risk events: replacement, large overlap, title conflict, multi-parcel adjustment, historical correction. | Use risk-based approval levels rather than one approval rule for every edit. | NLA / SMD | High-impact changes receive the same scrutiny as routine corrections. | Open
B-20 | Who performs reconcile/post to authoritative Enterprise data? | Technical | Critical | The workflow expects reconcile/post after approval, but final operational responsibility is not explicit. | Define whether system service account or authorized role executes posting. | Use controlled system-mediated post after approvals, with no discretionary direct production edit. | Joint Project Team | Approved edits may still be posted inconsistently or by unauthorized users. | Partially Defined
B-21 | Who resolves version/reconcile conflicts? | Governance | Critical | Concurrent transaction/version conflicts are expected. | Name technical/business authority and define retry/review procedure. | Do not auto-resolve material geometry conflicts; route to cadastral reviewer with before/after/current comparison. | NLA / SMD | One transaction may overwrite another transaction's valid change. | Open
B-22 | What happens if authoritative data changes while a transaction is under examination? | Business Rule | Critical | Versioned workspaces reduce risk but stale-reference handling needs formal rule. | Define when revalidation/Compare must rerun. | Material change to affected/adjacent parcels should invalidate prior Compare and require refresh/revalidation. | NLA / SMD | Decision may be based on obsolete cadastral context. | Open
B-23 | Must Compute/Compare be rerun after a material geometry change during review? | Business Rule | High | Not explicitly defined. | Approve rerun triggers. | Rerun affected geometry/topology/Compare checks whenever geometry changes after initial validation. | NLA / SMD | Final posted geometry may differ from what was actually validated. | Open
B-24 | What evidence is mandatory before replacement/merge/retirement? | Governance | Critical | Audit evidence is required conceptually but not standardized. | Define minimum evidence package. | Require source transaction, approved plan/document, discrepancy reason, before/after geometry, reviewer and approver. | NLA Joint | Authoritative changes cannot be defended later. | Open
B-25 | Is prior geometry permanently retained and queryable? | Data Policy | High | Versioning/lineage is expected but retention behavior should be approved. | Confirm historical geometry retention and access. | Preserve immutable lineage/history for every posted parcel lifecycle event. | NLA / SMD | Loss of historical cadastral evidence and audit trail. | Partially Defined
B-26 | How are downstream systems notified after posting? | Technical | High | Innola/LTD/LVD integration is architecturally anticipated. | Finalize event/status contract and synchronization responsibility. | Publish a committed-change event with affected PID(s), lineage and transaction ID. | Joint Project Team | Registry, valuation and spatial systems may become inconsistent after valid posting. | Partially Defined
B-27 | Who may reverse or correct a posted cadastral change? | Governance | Critical | A formal correction path is required but not fully defined. | Define correction transaction, authority and audit rules. | Never directly undo production history; use a new correction transaction preserving lineage. | NLA / SMD | Posted changes could be altered without traceable corrective process. | Open

## Lists
Status | Priority | Decision Owner | Decision Type
Open | Critical | NLA / SMD | Technical
Partially Defined | High | NLA / LTD | Business Rule
Defined | Medium | NLA / LVD | Governance
Closed | Low | NLA Joint | Cross-Division
|  | Sidwell | Data Policy
Innola
Joint Project Team